## Requirements
TASK |  |  |  | PERSON DAYS | 'Version' defines the different releases of the software.
Version 0: A requirement that we do not consider being implemented at this stage in any release of the software.
Development: |  |  |  | 1284 | Version 1: A requirement that should be implemented in the first release of the software.
Analysis: |  |  | 20% | 256.8 | Version 2: A requirement that should be implemented in an interim release of the software.
UI mockups: |  |  | 5% | 64.2 | Version 3: A requirement that should be implemented in the final/prod release of the software.
Technical design: |  |  | 10% | 128.4
Testing: |  |  | 15% | 192.6 | 'Priority' defines the order in which requirements will be implemented within a specific version. |  | Very High
Documentation: |  |  | 10% | 128.4 | Priority Low: Implementation at late stages of a version. |  | High
[5 empty] | Priority Medium: Implementation at middle stages of a version. |  | Medium
TOTAL: |  |  |  | 2054.4 | Priority High: Implementation at early/as-soon-as-possible stages of a version. |  | Low
Name | Version | Priority |  | Effort (pd) | Notes | Comments / Questions
REQ001 - Hardware environments | 1 | Medium |  | 0 | OPENWIS-SSD-001 The hardware environments must support Linux operating system. Mandatory: RHEL. Nice to have: CentOS, Ubuntu. | Non-Functional
REQ002 - System availability | 1 | Medium |  | 0 | OPENWIS-SSD-002 The system must support 99.9% availability. | Non-Functional
REQ003 - Product size | 1 | Medium |  | 0 | OPENWIS-SSD-013 OpenWIS must have the capability to collect, store and disseminate data and products whose size ranges between 1 bytes and 1 Gbytes in size. | Non-Functional
REQ004 - Data performance | 1 | Medium |  | 0 | OPENWIS-SSD-014 OpenWIS must have the capability to collect and store 30 Gbytes of data per day, and disseminate 50 Gbytes of data per day. | Non-Functional
REQ005 - Product performance | 1 | Medium |  | 0 | OPENWIS-SSD-015 OpenWIS must have the capability to ingest 50 products per second, assuming an average product size of 100KB and external software/hardware systems are not limitative. However, the range of product sizes is from 1KB to 500KB or bigger, with 5 times as many small products. | Non-Functional
REQ006 - Metadata performance | 1 | Medium |  | 0 | OPENWIS-SSD-019 System must support processing of 5 DAR metadata transactions per second. | Non-Functional
REQ007 - Concurrent users | 1 | Medium |  | 0 | OPENWIS-SSD-020 One system deployment must support 10,000 anonymous users and 2,000 authenticated users 'simultaneously'. | Non-Functional
REQ008 - Local authentication performance | 1 | Medium |  | 0 | OPENWIS-SSD-021 The time per local authentication process must not exceed 10 seconds. | Non-Functional
REQ009 - Software environments | 1 | Medium |  | 0 | OPENWIS-SSD-004 OpenWIS must use these software environments: - Operating System: Red Hat vTBD - Database: TBD - Java version: TBD - A/S (or servlet container): TDB | Non-Functional
REQ010 - Transport mechanism | 1 | Medium |  | 0 | OPENWIS-SSD-005 Transport mechanism must be TCP/IP. | Non-Functional
REQ011 - Docker | 1 | Medium |  | 0 | OPENWIS-SSD-006 Add requirement regarding docker (OpenWIS must be deployable in no more than 4 hours and upgradable in no more than 2 hours) | Included in Analysis task
REQ012 - Time synchronization | 1 | Medium |  | 0 | OPENWIS-SSD-007 All servers must be synchronized with NTP protocol on external time server. | Non-Functional
REQ013 - Text encoding | 1 | Medium |  | 0 | OPENWIS-SSD-008 OpenWIS must support text encode in the Unicode representation UTF-8. | Non-Functional
REQ014 - Timezone | 1 | Medium |  | 0 | OPENWIS-SSD-009 OpenWIS must be configured according to Universal Co-ordinated Time (UTC), independently of several local times world wide. For non-admins, a tooltip could be displayed to display local time. | Non-Functional
REQ015 - SSO | 1 | Medium |  | 0 | OPENWIS-SSD-011 Security service must support SSO. | This also exist in functional requirements. Estimation will placed there.
REQ016 - Data integrity | 1 | Medium |  | 0 | OPENWIS-SSD-012 OpenWIS must maintain the integrity of the data and metadata. | Non-Functional
REQ017 - Ingestion originator | 1 | Medium |  | 5 | OPENWIS-SSD-033 The condition for ingestion must possibly (via configuration) include a check of the originator.
REQ018 - Product checksum | 1 | Medium |  | 3 | OPENWIS-SSD-034 Checksum computation must be on a configurable number of non-white characters for a text product and on a configurable number of bytes for a binary product.
REQ019 - Duplicate checksums | 1 | Medium |  | 1 | OPENWIS-SSD-035 Duplicate with different checksum must not replace the previous bulletin instance. All different versions of a given bulletin instance should be kept. (What is the practical case of this?)
REQ020 - Ingestion of tmp files | 1 | Medium |  | 2 | OPENWIS-SSD-036 In order to facilitate FTP transfers, OpenWIS must not ingest files with a '.tmp' extension. This temporary drop suffix should be configurable. (This will apply to the API client)
REQ021 - Incoming file purge | 1 | Medium |  | 0 | OPENWIS-SSD-037 After ingesting a file containing data, OpenWIS must purge this file from the incoming directory used for collecting data from the MSS/FSS. | Included in REQ109
REQ022 - Product monitoring | 1 | Medium |  | 10 | OPENWIS-SSD-054 OpenWIS must allow known Institutional users to view all products currently routed to them by the local MSS/FSS. All visible routeing (subscriptions done via OpenWIS or not) will be monitored (viewed &amp; controlled) in OpenWIS.
REQ023 - Event monitoring | 1 | Medium |  | 5 | OPENWIS-SSD-056 OpenWIS must allow known all users to view recent product instances routed to them by the local MSS/FSS.
REQ024 - Collection API | 1 | Medium |  | 0 | OPENWIS-SSD-028 a) The System must provide a generic specified and documented interface/API b) An API client should be able to communicate with WMO compliant Message Switching Systems (MSS) and File Switching Systems (FSS). | Provided from GTS
REQ025 - API client support | 1 | Medium |  | 40 | OPENWIS-SSD-029 The generic interface/API client to the MSS / FSS must support: - The collection of GTS products, - The supply of products, - The submission of requests for changes in the product routeing,(the API client) - The monitoring of products currently routed to a given destination,(log file) - The monitoring of implemented routeing changes , (log file) - The monitoring of recent events concerning a given destination. (log file)
REQ026 - Dissemination failure | 1 | Medium |  | 5 | OPENWIS-SSD-099 When the transport mechanism or network solution compromise yields no appropriate solution, OpenWIS must send email to notify to the user it's failed . To avoid mail storm, send a few emails, flag the channel as “defective”, and the user may return and re-enable notifications
REQ027 - Dissemination request status | 1 | Medium |  | 5 | OPENWIS-SSD-098 OpenWIS must be able to display status, warnings and errors raised by the dissemination system while processing the request.
REQ028 - Dissemination transport mechanism | 1 | Medium |  | 20 | OPENWIS-SSD-095 The transport mechanism or network solution must be one parameter of the dissemination instructions transmitted to the dissemination system. The transport mechanism or network solution chosen by OpenWIS will be a configurable compromise betweenΒ : - The user dissemination choices - The SLA for the user - OpenWIS dissemination rules (e.g. for high volume data, no dissemination by email, etc) - The data GTS priority and data policy (both found in the metadata) (Get feedback concerning the value of high volume data)
REQ029 - Dissemination priority | 1 | Medium |  | 0 | OPENWIS-SSD-096 The priority of data must be one parameter of the dissemination instructions transmitted to the dissemination system. This priority is a compromise between: - the SLA for the user - the GTS Data priority (found in the metadata) OpenWIS (and not only the dissemination system) will manage priorities at its own level. | Included in REQ028
REQ030 - Ad-hoc dissemination transport | 1 | Medium |  | 0 | OPENWIS-SSD-097 The ad hoc request service must support the same transport mechanisms as the subscription service, with the exception of MSS/FSS Distribution. | Included in REQ034
REQ031 - Dissemination web service contract | 1 | Medium |  | 7 | OPENWIS-SSD-093 OpenWIS must define a generic Web Service contract (e.g. WSDL) that the dissemination system Harness will have to honour to make the dissemination services accessible. This is when the GISC sends data.
REQ032 - Current request status | 1 | Medium |  | 5 | OPENWIS-SSD-077 OpenWIS must allow authenticated and authorized users of a Centre to check the status of their current requests from that Centre, either ad-hoc or subscription implemented by OpenWIS and by the local MSS/FSS.
REQ033 - Subscription details management | 1 | Medium |  | 18 | OPENWIS-SSD-079 Authorized and authenticated users must be able to manage their own subscription details. 'Manage' means here : modify details, pause, delete, provided the subscription was composed locally (no administration of subscriptions composed at another Centre) The error message will be captured and displayed to the user. If the underlaying API/service supports it
REQ034 - Creation of ad-hoc requests | 1 | Medium |  | 20 | OPENWIS-SSD-072 OpenWIS must allow authenticated and authorized users to make requests for products (either locally cached in the Cache (for GISCs only) or locally produced) on an ad-hoc basis.
REQ035 - Ad-hoc request delivery | 1 | Medium |  | 0 | OPENWIS-SSD-073 Ad-hoc requests sent to OpenWIS must be synchronous for web delivery and asynchronous via dissemination Harness. | Included in REQ034
REQ036 - Ad-hoc request destinations | 1 | Medium |  | 0 | OPENWIS-SSD-074 OpenWIS must allow the user to specify primary destination details (i.e. host, location, network) for its ad-hoc requests. | Included in REQ034
REQ037 - Request processing | 1 | Medium |  | 10 | OPENWIS-SSD-080 OpenWIS must be able to process (ad-hoc and subscription) requests on a scheduled basis.
REQ038 - Processing on data availability | 1 | Medium |  | 10 | OPENWIS-SSD-081 OpenWIS must be able to process subscriptions when new data/products are available. Requests should support multiple products. Subscriptions should support multiple metadata records/data-sets
REQ039 - Subscription request creation | 1 | Medium |  | 5 | OPENWIS-SSD-075 OpenWIS must allow authenticated and authorized users to make requests for products (to which they are authorized) (either locally cached in the Cache (for GISCs only) or locally produced) as a recurrent subscription.
REQ040 - Subscription request destinations | 1 | Medium |  | 5 | OPENWIS-SSD-076 OpenWIS must allow the user to specify primary and alternate destination details (i.e. host, location, network) for its subscription requests
REQ041 - Subscription monitoring | 1 | Medium |  | 0 | OPENWIS-SSD-083 OpenWIS must allow Authorized Administrators (AccessAdmins) to monitor all subscriptions. | Included in REQ042
REQ042 - Subscription administrational operations | 1 | Medium |  | 20 | OPENWIS-SSD-084 OpenWIS must allow Authorized Administrators (AccessAdmins) to administer all subscriptions. 'Administration operations' include: checking/modifying details, pause, post warning to the user on his request monitoring page, deletion of subscription.
REQ043 - Product request status | 1 | Medium |  | 10 | OPENWIS-SSD-090 OpenWIS must be able to check the status of a request for an instance of a product on a local data source. | Includes effort for familiarisation with GTS API
REQ044 - Product dissemination preparation | 1 | Medium |  | 15 | OPENWIS-SSD-092 OpenWIS must be able to prepare an extracted product for dissemination, associating the generated product file to the user request, along with dissemination instructions. Preparation can additionally (user choice) include a change of format: e.g. several instance files packed in a zip, or WMO-FTP encapsulation. | Includes effort for familiarisation with GTS API
REQ045 - Retrieval web service contract | 1 | Medium |  | 7 | OPENWIS-SSD-085 OpenWIS must define a generic Web Service contract that each local data source Harness will have to honour to make its data accessible. This is for when GISC receives data.
REQ046 - Harness testing examples | 1 | Medium |  | 15 | OPENWIS-SSD-086 To facilitate testing of deployed system and implementation of Harness, OpenWIS must be provided with dummy examples of Harness (stubs) for access to: a file system, a database, a call to another Web Service and a script call.
REQ047 - Global data | 1 | Medium |  | 2 | OPENWIS-SSD-027 Essential Data, Additional Data or Local Data must be distinguished thanks to its GTS Category described in its associated metadata.
REQ048 - Metadata creation | 0 | Medium |  | 0 | OPENWIS-SSD-130 OpenWIS must provide a facility for an authorized user to create new metadata records. (Not required for version 1) | Excel2WIS, or GeoNetwork, or a combination of them
REQ049 - Metadata deletion | 1 | Medium |  | 2 | OPENWIS-SSD-134 OpenWIS must provide the ability for authenticated and authorized users to delete metadata records.
REQ050 - Metadata editor | 0 | Medium |  | 0 | OPENWIS-SSD-131 OpenWIS must provide a Web based metadata editor allowing the editing of metadata records. (Not required for version 1)
REQ051 - Metadata editor codelists | 1 | Medium |  | 15 | OPENWIS-SSD-132 Metadata editor must support codelists facility, allowing the restriction of field values to value domain lists. | Includes associating xsd attributes with closed-lists
REQ052 - Metadata editor suggestions | 1 | Medium |  | 5 | OPENWIS-SSD-133 Metadata editor must support a suggestion mechanism, providing proposed domain values for specified fields during editing.
REQ053 - Dataset metadata support | 1 | Medium |  | 0 | OPENWIS-SSD-101 OpenWIS must support metadata for datasets implementing WMO Core Profile of ISO 19115:2003 (Get the current state of the relevant ISOs) | Non-Functional
REQ054 - Service metadata support | 1 | Medium |  | 0 | OPENWIS-SSD-102 OpenWIS must support metadata for service implementing ISO 19119:2006. | Non-Functional
REQ055 - Metadata URN | 1 | Medium |  | 0 | OPENWIS-SSD-103 Metadata records in the OpenWIS DAR catalogue must be uniquely identified by a specific Uniform Resource Name (URN). | Included in REQ048
REQ056 - Metadata record relationships | 1 | Medium |  | 0 | OPENWIS-SSD-104 The OpenWIS system must provide the ability to handle metadata records having a one to many relationships with the corresponding data or product, but also a one-to-one correspondence with data records. | Non-Functional
REQ057 - Product classes and instances | 1 | Medium |  | 15 | OPENWIS-SSD-105 It must be possible in OpenWIS to distinguish between a class of products and a product instance. A saved search mechanism will allow easier management of product classes.
REQ058 - Metadata processing size | 1 | Medium |  | 0 | OPENWIS-SSD-106 OpenWIS system must manage at least a number of 500000 DAR metadata records for its catalogue, with associated indexed fields and keywords. | Non-Functional
REQ059 - CSW support | 1 | Medium |  | 20 | OPENWIS-SSD-126 OpenWIS must be able to harvest DAR metadata from remote sources using the protocol Catalogue Service for the Web (CSW) version 2.0.2. (Not required now but for WIS version 2)
REQ060 - OAI/PMH support | 1 | Medium |  | 15 | OPENWIS-SSD-127 OpenWIS must be able to harvest DAR metadata from remote sources using the protocol OAI-PMH.
REQ061 - DC/FGDC support | 1 | Medium |  | 10 | OPENWIS-SSD-128 OpenWIS must be able to harvest metadata records in all locally defined profiles of ISO19115:2003, ISO 19119:2006, Dublin-Core (DC) and Federal Geographical Data Committee (FGDC).
REQ062 - Harvesting management | 1 | Medium |  | 15 | OPENWIS-SSD-129 OpenWIS must provide means to manage harvesting, allowing administrators to create, modify or remove harvesting tasks with other sources.
REQ063 - Metadata record export | 1 | Medium |  | 5 | OPENWIS-SSD-120 OpenWIS must provide a metadata record export facility. (Also bulk export for admins only)
REQ064 - Metadata record export format | 1 | Medium |  | 15 | OPENWIS-SSD-121 OpenWIS must provide the ability to export metadata records selected in XML format or in Metadata Export Format (MEF).
REQ065 - Metadata record export conformance | 1 | Medium |  | 5 | OPENWIS-SSD-122 OpenWIS must be able to export metadata records as most current version of WMO Core Profile conformant records, provided a conversion XSLT is available for the native profile of the harvested/imported metadata. Will support the required export formats.
REQ066 - Metadata record export in own standard | 1 | Medium |  | 30 | OPENWIS-SSD-123 OpenWIS must be able to export profile conforming metadata records according to their own standard. | It includes effort to specify the actual format
REQ067 - Metadata record import | 1 | Medium |  | 20 | OPENWIS-SSD-116 OpenWIS must provide a metadata record import facility.
REQ068 - Metadata record import format | 1 | Medium |  | 10 | OPENWIS-SSD-117 Metadata records must be imported into OpenWIS in XML format or Metadata Export Format (MEF). | Investigation for MEF is included in REQ064
REQ069 - Metadata record import conformance | 1 | Medium |  | 20 | OPENWIS-SSD-118 OpenWIS import facility must support metadata record imports in all locally defined profiles of ISO19115:2003, ISO 19119:2006, Dublin-Core (DC) and Federal Geographical Data Committee (FGDC).
REQ070 - Unsupported metadata record import | 1 | Medium |  | 15 | OPENWIS-SSD-119 OpenWIS must be able to import unsupported metadata in XML format by applying a predefined XSL transformation.
REQ071 - Metadata record validation | 1 | Medium |  | 20 | OPENWIS-SSD-110 OpenWIS must provide a metadata record validation process.
REQ072 - Metadata validation rules | 1 | Medium |  | 0 | OPENWIS-SSD-111 Metadata validation must be processed against XML schema validation (XSD) but also against specific rules to be compliant with the version 1.1 of the WMO Core Profile of ISO 19115:2003. | Included in REQ074
REQ073 - Harvested metadata validation | 1 | Medium |  | 5 | OPENWIS-SSD-112 Harvesting mechanism must invoke a metadata validation before inserting records into the DAR catalogue. | Will reuse code from REQ071
REQ074 - Harvested metadata validation level | 1 | Medium |  | 25 | OPENWIS-SSD-113 Metadata validation level must be configurable as a function of the harvested source. Different configured levels are: no validation, XSD validation only or full validation including validation against XSD schema and schematron rules. Existing schematron validation rules: https://github.com/OpenWIS/openwis/blob/master/openwis-metadataportal/schematrons/rules/schematron-rules-iso.sch | Includes of the integration of schematron to the application.
REQ075 - Metadata validation by profile | 1 | Medium |  | 0 | OPENWIS-SSD-114 OpenWIS metadata editor facility must provide support for validating metadata records against their profile. | Included in REQ071
REQ076 - Metadata element validation | 1 | Medium |  | 10 | OPENWIS-SSD-115 OpenWIS validation process must provide a mechanism to check if metadata elements (values) are in expected value domain lists.
REQ077 - Controlled vocabularies | 0 | Medium |  | 0 | OPENWIS-SSD-124 OpenWIS must handle controlled vocabularies files as RDF thesauri (closed-lists) in Simple Knowledge Organization System (SKOS) format.
REQ078 - Closed-list maintenance | 1 | Medium |  | 10 | OPENWIS-SSD-125 OpenWIS must provide support for the maintenance of thesauri (closed-lists). Thesauri management will allow administrators to upload / edit / remove thesaurus through the administration page.
REQ079 - Metadata integrity | 1 | Medium |  | 0 | OPENWIS-SSD-107 OpenWIS must maintain the integrity of metadata records during basic operations such as search, visualization, harvesting, synchronization and metadata validation. | Non-Functional
REQ080 - Metadata handling ISO | 1 | Medium |  | 0 | OPENWIS-SSD-108 OpenWIS must handle metadata records in the version 1.1 of the WMO Core Profile of ISO 19115:2003. (Check if version 1.1 is current) | Covered In REQ048 as long as there is an xsd provided.
REQ081 - Extensible metadata support | 1 | Medium |  | 0 | OPENWIS-SSD-109 OpenWIS must be extensible in order to implement any new metadata profile such as the next version of the WMO Core Profile or the Marine Community Profile. | Non-Functional
REQ082 - Thesaurus (closed-list) search | 1 | Medium |  | 20 | OPENWIS-SSD-145 OpenWIS must support hierarchical keyword search based on thesaurus (closed-list) relations where terms are related as broader / narrower than.
REQ083 - CSW search | 1 | Medium |  | 20 | OPENWIS-SSD-139 OpenWIS metadata catalogue must be able to be queried using the CSW standard, version 2.0.2.
REQ084 - SRU search | 1 | Medium |  | 20 | OPENWIS-SSD-140 OpenWIS must support searches according to ISO 23950 using SRU profile version 1.2.
REQ085 - Keyword search | 1 | Medium |  | 60 | OPENWIS-SSD-141 OpenWIS must supports searching on keywords, subject terms, spatial bounding boxes and date ranges (dateTime). | Includes the implementation of the search engine module
REQ086 - Search extensibility | 1 | Medium |  | 20 | OPENWIS-SSD-142 OpenWIS search facility and search mechanism must be extensible enough to configure search on any set of elements within all standards supported by the system.
REQ087 - Spatial search | 1 | Medium |  | 5 | OPENWIS-SSD-143 OpenWIS must support spatial searches on spatial bounding box in Spatial Reference System (SRS) WGS84 as standard (EPSG:4326).
REQ088 - Fuzzy search | 1 | Medium |  | 3 | OPENWIS-SSD-144 OpenWIS must support tolerant search such as fuzzy search and not only exact search. The tolerance rate must be configurable. | Based on the Fuzzy search functionality of the underlying search engine
REQ089 - Catalogue re-creation | 1 | Medium |  | 3 | OPENWIS-SSD-138 OpenWIS must allow the re-creation of a GISC DAR metadata catalogue from another specified GISC, based on the synchronization mechanism. | Reuses REQ062
REQ090 - Metadata synchronization | 1 | Medium |  | 10 | OPENWIS-SSD-137 OpenWIS synchronization mechanism will rely on harvesting processes defined and configured on each synchronized centres, using OAI-PMH protocol. Synchronization should be supported for all protocols, as long as the protocol itself supports it. | Quoted effort covers OAI-PMH as effort to support additional protocols is not know at this moment
REQ091 - Synchronization tasks | 1 | Medium |  | 3 | OPENWIS-SSD-135 OpenWIS must provide means to manage synchronization, allowing administrators to create, modify or remove synchronization tasks with other OpenWIS GISCs. Any potential synchronization errors must be reported in the management interface | Reuses REQ090
REQ092 - Admin interface | 1 | Medium |  | 0 | OPENWIS-SSD-202 OpenWIS must provide an integrated user interface to enable authorized Administrators and Operators to control the functions of the System. | Non-Functional
REQ093 - Operator actions | 1 | Medium |  | 15 | OPENWIS-SSD-203 OpenWIS must enable authorised operator to: - Stop and start flow of data to and from the local GISC node (ingestion and dissemination) - Stop and start data replication and synchronisation between the local and partner GISC nodes - Stop and start metadata replication and synchronisation between the local and partner GISC nodes - Stop and start metadata harvesting process on the local GISC node - Disable and enable portal service on the local GISC node - Stop and start all services (metadata and data synchronization, metadata harvesting and user portal) on the local node GISC node - Stop and start flow of data to and from the local GISC node and connected users - Stop and start request processing for a given user group
REQ094 - Alarm functions | 1 | Medium |  | 20 | OPENWIS-SSD-194 OpenWIS must provide configurable alarm function which will produce warning messages when pre-defined thresholds are exceeded or the following defined events occur: - The failure of any single system function ( main controlled functions, see controlling section) - The loss or corruption of data (plug-in allowing to check corrupted data will raise an alarm) - The loss or corruption of metadata (alarm raised when validation fails) - The ingestion of products which are greater than 1 GBytes in size - The ingestion of data for which no metadata record exists (Needs to be logged separately form alarm system) - When the size of the data Cache exceeds a defined value - When harvested metadata records fail schema validation (One alert per harvesting/sync execution and not per metadata) - When Administrators and Operators fail authentication - When any unauthorised access to the system is attempted (Access to the API without a token, and also brute-force login) - When the number of active authenticated users exceeds a defined threshold - When the number of active anonymous users exceeds a defined threshold - When delivery fails (error, warning raised by the dissemination system) - Failure to contact a local data source or when extraction fails - When a user requests an extension of privileges The alert limits must be configurable (Where applicable) and the application should allow to activate/deactivate alerts globally.
REQ095 - Alarm logging | 1 | Medium |  | 2 | OPENWIS-SSD-195 The alarms must be logged in one or several predefined log file(s). The alarm log file will be in a defined common format. (Consider JSON)
REQ096 - Alarm events view | 1 | Medium |  | 25 | OPENWIS-SSD-196 The alarms log events must be viewed within a web page. The number and levels of displayed alarms must be configurable. Define a monitoring API for other systems can use.
REQ097 - Alarm management | 1 | Medium |  | 3 | OPENWIS-SSD-197 OpenWIS must manage the alarms of a local distributed system only.
REQ098 - Action logging | 1 | Medium |  | 6 | OPENWIS-SSD-198 OpenWIS must be capable of logging details for each action that modifies the databases, the configuration parameters, the content of the Cache or generally all actions inducing persistent changes. Application will also audit user sign-in /sign-out.
REQ099 - Log-file naming | 1 | Medium |  | 1 | OPENWIS-SSD-199 The log files must be rolling files with a backup number of days and a filename pattern including the date. | Supported by the configuration of the underlying server
REQ100 - Monitoring functions | 1 | Medium |  | 10 | OPENWIS-SSD-192 OpenWIS must provide monitoring functions of distributed components to be used by Operators and/or Administrators. (Add service statuses, graphs, etc. Provide verbose info. Consider Kibana) | Quoted effort is for the implementation of the mechanism; will be augmented according to the number of reports to be created.
REQ101 - Monitoring severity levels | 1 | Medium |  | 0 | OPENWIS-SSD-193 OpenWIS must support different levels of severity of event, such as Information, Warning, and Critical. | Included in REQ100
REQ102 - Report creation | 1 | Medium |  | 10 | OPENWIS-SSD-200 OpenWIS must be able to produce reports, on request from an authorised user, based on the logs and events contained in available log files or database. Reports will be integrated in the Administration Portal and can be exported in XML, and filtered as a function of parameters specified by the Operator. Report contents should be kept for several years. (XML format is under consideration)
REQ103 - Report types | 1 | Medium |  | 20 | OPENWIS-SSD-201 The following reports must be available: - Overall availability (daily percentage of availability) of local GISC node for a given period (day, week, month, year) - Availability of each service component of local GISC node - Overall volume of data replicated per day and per GISCs - Overall volume of data ingested and disseminated per day - Volume of data disseminated per authorised user and per day - Overall volume of metadata harvested or synchronized per day and per Centre (e.g. DCPCs, NCs) - Overall activity per day of the User Portal (for example number of opened sessions)
REQ104 - Reports page | 1 | Medium |  | 20 | OPENWIS-SSD-302 OpenWIS must provide a page that shows the following reports for a selectable period: - Number of opened sessions per day - Volume and number of harvested/synchronized/created metadata per day and per source (harvesting source, synchronization source, locally created) - Volume of data disseminated per day and per user - Volume of data disseminated and extracted per day - Volume of data ingested per day - Volume of data replicated per source and per day
REQ105 - Recent alarms | 1 | Medium |  | 0 | OPENWIS-SSD-301 OpenWIS must display the list of recent alarms in table that can be sorted and filtered. | Included in REQ096
REQ106 - System availability page | 1 | Medium |  | 5 | OPENWIS-SSD-343 OpenWIS must provide a page that shows the availability of the main functions of the local system, including the following information: - status of the main functions of the Metadata Service (synchronization, harvesting, index) - status of the main functions of the Data Service (replication, ingestion, request processing) - status of the security services
REQ107 - Service control | 1 | Medium |  | 5 | OPENWIS-SSD-344 On the Availability of Local System page, it must be possible to: - start/stop all the local services - start/stop all the metadata services - start/stop all the data services
REQ108 - Cache parameter control | 1 | Medium |  | 5 | OPENWIS-SSD-326 OpenWIS must provide a page allowing an Operator to configure the following Cache parameters: - MSS/FSS Ingestion
REQ109 - Ingestion control | 1 | Medium |  | 20 | OPENWIS-SSD-327 To configure ingestion, OpenWIS must allow: - to globally enable / disable ingestion | This estimate includes the ingestion mechanism itself.
REQ110 - Cache content display | 1 | Medium |  | 15 | OPENWIS-SSD-330 OpenWIS must provide a table showing the Cache content including for each file: - the file name - the checksum - the origin, indicating from where the file has been replicated (if possible) - the metadata ID - insertion date - HTTP Download from the cache (like Ad hoc)
REQ111 - Cache statistics page | 1 | Medium |  | 6 | OPENWIS-SSD-332 OpenWIS must provide a statistics page for the Cache, including the following information: - a table (sort-able and filterable) showing the volume of data ingested per day - a table (sort-able and filterable) showing the volume of data replicated per source and per day - Size of the cache at 0:00 UTC every day - Number of products in the cache at 0:00 UTC every day
REQ112 - Current request monitoring page | 1 | Medium |  | 7 | OPENWIS-SSD-320 The page 'Monitor Current Requests' must allow an AccessAdmin or an Operator user to list: - all the current ad-hoc requests and requests generated as instances of a subscription request - all the subscription Administrator may edit any user settings in subscriptions
REQ113 - Request monitoring filtering | 1 | Medium |  | 5 | OPENWIS-SSD-321 It must be possible to filter the list of requests and subscription by a selection of user groups, which will result in showing the requests (ad-hoc and subscription) issued by users belonging to the selected groups. Filtering should be extended to the level of single users.
REQ114 - Ad-hoc request management | 1 | Medium |  | 5 | OPENWIS-SSD-322 The AccessAdmin or an Operator must be able to View details and Discard an ad-hoc request.
REQ115 - Subscription management | 1 | Medium |  | 5 | OPENWIS-SSD-323 The AccessAdmin or an Operator must be able to Edit, Suspend and Discard a subscription.
REQ116 - Request statistics | 1 | Medium |  | 5 | OPENWIS-SSD-324 OpenWIS must provide a statistics page for the Requests, including the following information: - a table (sort-able and filterable) showing the volume of data disseminated per day and per user - a table (sort-able and filterable) showing the volume of data disseminated and extracted per day (Generally improve "request statistics") | Reuses REQ111
REQ117 - User form linking | 1 | Medium |  | 1 | OPENWIS-SSD-325 Clicking on a user of the User table column must lead to the user form, allowing to edit: - Global and per-subscription switch to manage dissemination. - Disable user from signing-into the system.
REQ118 - Admin portal home page | 1 | Medium |  | 3 | OPENWIS-SSD-300 The Home Page of the Administration portal must display: - an information HTML content if user is not authenticated or not authorized, - accessible functions if user is authenticated and authorized and the recent alarms function selected by default.
REQ119 - Add metadata page | 1 | Medium |  | 0 | OPENWIS-SSD-303 OpenWIS must provide an Add Metadata page that allows users with appropriate privileges to create a new metadata or to import metadata from existing file(s) | Included in REQ048 and REQ067
REQ120 - Harvesting task management | 1 | Medium |  | 0 | OPENWIS-SSD-304 OpenWIS must provide a page to administrate the harvesting tasks, including the following actions: - Create a new Harvesting task - Modify an existing Harvesting task - Delete an Harvesting task - Activate/Deactivate an Harvesting task - Run (immediately) an Harvesting task | Included REQ062
REQ121 - Harvesting task form | 1 | Medium |  | 0 | OPENWIS-SSD-305 The harvesting task form must allow to set the following details: - the harvesting source - the harvesting protocol, including credentials - alternative search criteria ( = sources list) - schedule parameters (synchronization only '“ similar to CGN 3.2.X) - level of validation - remote Category (OAI-PMH) - local Categories | Included REQ062
REQ122 - Synchronization task management | 1 | Medium |  | 0 | OPENWIS-SSD-306 OpenWIS must provide a page to administrate the Synchronization tasks, including the following actions: - Create a new Synchronization task - Modify an existing Synchronization task - Delete an Synchronization task - Activate/Deactivate an Synchronization task - Run (immediately) an Synchronization task (As parameters of harvesting task) | Included in REQ090
REQ123 - Monitor catalogue content | 1 | Medium |  | 10 | OPENWIS-SSD-308 OpenWIS must provide a page that lists all the metadata contained in the catalogue (alternatively in a paginated way), showing the following metadata information: - metadata ID (URN) - metadata title - Process (process which created this metadata '“ harvesting/synchronization/local creation) - Originator - GTS Category - AHL pattern or overridden AHL pattern if any - FNC pattern or overridden FNC pattern if any - GTS priority - Data policy or overridden data policy if any - Local Data source where the data comes from - Whether the product will be ingested on the current deployment - Whether the product will be fed to the MSS/FSS on the current deployment - File extension or overridden file extension - Last modified date (Tabular form of browsing the products [nice to have a show/hide columns, move, sort, etc.])
REQ124 - Monitor catalogue content filtering | 1 | Medium |  | 5 | OPENWIS-SSD-309 The page Monitor Catalogue Content must provide a simple text-based functionality that filters the table of metadata. Combined filtering on any field.
REQ125 - Monitor catalogue content actions | 1 | Medium |  | 5 | OPENWIS-SSD-310 The page Monitor Catalogue Content must provide the following actions for each metadata: - View the details of a metadata - Remove the selected metadata (possibly bulk several metadata) - Export the selected metadata (possibly bulk metadata)
REQ126 - Monitor catalogue content metadata count | 1 | Medium |  | 0 | OPENWIS-SSD-311 The page Monitor Catalogue Content must display the number of metadata currently displayed (considering filter/search criteria). | Included in REQ123
REQ127 - MetaInfo form | 1 | Medium |  | 0 | OPENWIS-SSD-312 The MetaInfo form must allow to set the following details: - the overridden GTS Category - the overridden Data Policy - the overridden AHL pattern - the overridden FNC pattern - the GTS priority - the overridden file extension | Included in REQ125
REQ128 - MetaInfo form ingestion action | 1 | Medium |  | 15 | OPENWIS-SSD-313 The MetaInfo form must allow to add the selected metadata URN (possibly several metadata) to the list of ingestion filter. Define a widget that will allow “conditional” ingestion of data based on a user choice. May define a regex for matching, or through regular URN.
REQ129 - Catalogue statistics page | 1 | Medium |  | 5 | OPENWIS-SSD-315 OpenWIS must provide a statistics page for the Catalogue, including the following information: - the Catalogue size - the total number of metadata - a table (sort-able and filterable) showing the volume of metadata harvested, synchronized or locally created per day and per source
REQ130 - Template administration page | 1 | Medium |  | 10 | OPENWIS-SSD-316 OpenWIS must provide a page to administrate the templates, allowing the following functionalities: - Create a template - Insert a template - Sort the list of proposed templates (during creation) - Delete a template (Templates are shared among all users of the system)
REQ131 - Index administration page | 1 | Medium |  | 10 | OPENWIS-SSD-317 OpenWIS must provide a page to administrate the index, allowing the following functionalities: - Rebuild the index - Optimize the index
REQ132 - Category management | 1 | Medium |  | 10 | OPENWIS-SSD-319 OpenWIS must provide a page to administrate the Categories, allowing the following functionalities: - Add a Category - Edit a Category - Delete a Category Show alert regarding existing subscribers in categories to be deleted.
REQ133 - Thesauri (closed-list) management | 1 | Medium |  | 0 | OPENWIS-SSD-318 OpenWIS must provide a page to administrate the Thesauri (closed-lists), allowing the following functionalities: - Add a Thesaurus - Delete a Thesaurus | Included in REQ078
REQ134 - Data policy actions | 1 | Medium |  | 10 | OPENWIS-SSD-340 An AccessAdmin must be able to list, create, edit, and delete data policies.
REQ135 - Data policy export | 1 | Medium |  | 10 | OPENWIS-SSD-341 An AccessAdmin to export a selection of data policies as XML, including details of the data policies (groups/operations) only for SSO groups.
REQ136 - Data policy form | 1 | Medium |  | 0 | OPENWIS-SSD-342 The Data Policy Form must allow to set: - the name of the Data Policy - a description - the operations allowed for each group - a list of alias that can be found in the metadata, to consider as equivalent as the edited data policy (check if a related tag exists in the xml) | Included in REQ134
REQ137 - Group management | 1 | Medium |  | 5 | OPENWIS-SSD-338 An AccessAdmin or an Administrator must be able to list, create, edit, and delete Groups. (!!! Careful Profile is not the same as Group . EX: The Profile might be Editor and the Group might be Institutional !!!)
REQ138 - Group SSO | 1 | Medium |  | 0 | OPENWIS-SSD-339 Group editor must allow to set if the group can be used (granted) when doing SSO. | Included in REQ137
REQ139 - User management | 1 | Medium |  | 20 | OPENWIS-SSD-333 An AccessAdmin or an Administrator must be able to list, create, edit, and delete Users. (Generally improve SSO management) (Improve user management, Separate admin/ user portal, same s/w different options) | Includes the API for transparent access to the user repository
REQ140 - User filtering by group | 1 | Medium |  | 2 | OPENWIS-SSD-334 It must be possible to filter the list of by a selection of user groups, which will result in showing the users belonging to the selected groups.
REQ141 - Self-registered user management | 1 | Medium |  | 0 | OPENWIS-SSD-335 An AccessAdmin or an Administrator must be able to list, edit or discard users that have requested to be registered (self-registration function). It must be possible to configure OpenWIS to disable self registration. | Included in REQ151
REQ142 - User form | 1 | Medium |  | 3 | OPENWIS-SSD-336 In addition to the user information and the favourite disseminations, the admin User Form must allow to edit: - the user profile (user, editor, administrator, '¦) - the user groups
REQ143 - User form actions | 1 | Medium |  | 5 | OPENWIS-SSD-337 The admin User form must allow an AccessAdmin to: - send an email to the user - accept or discard the request to elevate the users privileges (Add a page to manage elevation requests)
REQ144 - Localization | 1 | Medium |  | 10 | OPENWIS-SSD-348 An Administrator must be able to manage localized strings stored in database.
REQ145 - Managment of pre-defined parameters | 1 | Medium |  | 5 | OPENWIS-SSD-347 An Administrator must be able to manage system pre-defined parameters
REQ146 - Administration portal access | 1 | Medium |  | 0 | OPENWIS-SSD-299 Administration portal must be accessible only for Administrator, Operators and AccessAdmin. | Is included in REQ118
REQ147 - Extension of privileges | 1 | Medium |  | 10 | OPENWIS-SSD-216 When a user tries to perform an unauthorized action, an error message must be displayed. This error message must propose to request for an extension of privilege to the Administrator (mail). (Add features: 1. Send user information in email. 2. Open a page with a list of pending requests)
REQ148 - Login | 1 | Medium |  | 1 | OPENWIS-SSD-212 Login is accessible from the header, including login, password and user domain
REQ149 - Logout | 1 | Medium |  | 1 | OPENWIS-SSD-213 Logout is performed from the header.
REQ150 - Self-registration request | 1 | Medium |  | 1 | OPENWIS-SSD-214 If the administrator has activated the self-registration mechanism, OpenWIS must allow a user to request for registration.
REQ151 - Self-registration workflow | 1 | Medium |  | 10 | OPENWIS-SSD-215 The registration workflow must be the following: - the user requests for registration by filling the registration form - Email verification after user self-registration (at this point the user can login as a guest) - a mail is sent to the Administrator and a registration request is stored in OpenWIS - the Administrator accept/discard the registration and set the user privileges - a mail is sent to the User to indicate the result of his registration - if accepted, the User can log into the System
REQ152 - Web-based | 1 | Medium |  | 0 | OPENWIS-SSD-204 OpenWIS must be a Web-based application (Responsive design) | Non-Functional
REQ153 - Design pattern | 1 | Medium |  | 0 | OPENWIS-SSD-205 OpenWIS portal must be based on an MVC-like (Model / View / Controller) framework. (Under consideration) | Non-Functional
REQ154 - Scalability | 1 | Medium |  | 0 | OPENWIS-SSD-206 OpenWIS portal must support scalability. | Non-Functional
REQ155 - Portal header | 1 | Medium |  | 0 | OPENWIS-SSD-207 The portal header must contain the OpenWIS logo and the Partner logo, as well as a title of the local Centre. | Is inculded REQ118 and REQ169
REQ156 - Configurable look'n'feel | 1 | Medium |  | 0 | OPENWIS-SSD-208 OpenWIS portal must be configurable in terms of 'look and feel' by modification of the resource files, images (including Partner logo in header) and style sheets. | Non-Functional
REQ157 - Multi-language support | 1 | Medium |  | 0 | OPENWIS-SSD-209 OpenWIS Portal must be configurable in terms of language (multi-language support) and allows the User to select his current language among supported languages. The default portal will be packaged and delivered with the English version. | Non-Functional
REQ158 - Portals | 1 | Medium |  | 0 | OPENWIS-SSD-210 OpenWIS must provide 2 separate portals: - User portal: covers functionalities accessible by non-authenticated and authenticated Users - Administration portal: covers functionalities accessible by authenticated Operators, AccessAdmin and Administrators | Non-Functional
REQ159 - Users | 1 | Medium |  | 0 | OPENWIS-SSD-211 OpenWIS must support authenticated and authorized users, as well as public or 'guest' users. | Non-Functional
REQ160 - Target browsers | 1 | Medium |  | 0 | OPENWIS-SSD-217 The targeted browsers are IE, Firefox, Chrome (all latest versions) | Non-Functional
REQ161 - Portal resolution | 1 | Medium |  | 0 | OPENWIS-SSD-218 The minimum portal resolution must be 1024 x 768, but it should be fully functional for other resolutions. | Non-Functional
REQ162 - Web technologies | 1 | Medium |  | 0 | OPENWIS-SSD-219 The Web-based interfaces will make an adequate usage of the following technologies: CSS v2.0, XHTML v1.0, XSLT v2.0, RSS v1.0, JSP v2.0, ExtJS 3.0, GeoExt 0.7 and OpenLayers 2.9. (Update technologies) | Non-Functional
REQ163 - HTTPS | 1 | Medium |  | 0 | OPENWIS-SSD-220 OpenWIS portal must support HTTPS configuration. | Non-Functional
REQ164 - Cookies | 1 | Medium |  | 0 | OPENWIS-SSD-221 Persistent cookies must not be used within OpenWIS portal. | Non-Functional
REQ165 - ActiveX / applets | 1 | Medium |  | 0 | OPENWIS-SSD-222 OpenWIS portal must not use ActiveX or applets. | Non-Functional
REQ166 - Advanced search | 1 | Medium |  | 2 | OPENWIS-SSD-230 The advanced search component must propose to define complex search criteria, including: - content criteria (specific metadata elements: title, abstract, keywords) - geographical criteria - temporal criteria | Includes only UI customisations (the search service will reused from REQ048)
REQ167 - Metadata editing | 1 | Medium |  | 0 | OPENWIS-SSD-234 Metadata editing might rely on the GeoNetwork Editor. | Included in REQ050
REQ168 - Metadata visualization | 1 | Medium |  | 15 | OPENWIS-SSD-235 Metadata visualization must be accessible from the result list.
REQ169 - User portal home page look'n'feel | 1 | Medium |  | 0 | OPENWIS-SSD-224 OpenWIS Home Page (User and Administration) must have its own original look & feel. | Included in REQ139
REQ170 - User portal home page simple search | 1 | Medium |  | 3 | OPENWIS-SSD-225 The Home Page must contain a screen area that provides a simple search (activated by default) that can be switched to an advanced search (unveiling extended search criteria). | Includes only UI customisations (the search service will reused from REQ048)
REQ171 - User portal home page advanced search | 1 | Medium |  | 3 | OPENWIS-SSD-226 It must be possible to configure OpenWIS to show the advanced search by default instead of the simple one. | Includes only UI customisations (the search service will reused from REQ048)
REQ172 - User portal home page recent changes | 1 | Medium |  | 5 | OPENWIS-SSD-227 The Home Page must contain a screen area that displays recent changes; including the last metadata updates and the recent requested products. (This component may be added in 228)
REQ173 - User portal home page widgets | 1 | Medium |  | 10 | OPENWIS-SSD-228 The Home Page must contain a screen area containing configurable information (Add widgets like 'latest subscriptions', or 'alert widget')
REQ174 - Keyword selection | 1 | Medium |  | 10 | OPENWIS-SSD-231 The Keywords search accessible from the advanced search must be enhanced with a tool that enables the user to select keywords coming from thesaurus, displayed hierarchically.
REQ175 - Request creation wizard | 1 | Medium |  | 0 | OPENWIS-SSD-236 If the user clicks on 'Request' or 'Subscribe" for a product served by the local OpenWIS node, the System must display the request creation wizard. | Broken down in REQ195 and REQ196
REQ176 - Request redirection | 1 | Medium |  | 3 | OPENWIS-SSD-237 If the user clicks on an action associated with a CI_OnlineResource for a product that is not local to the current Centre, the user must be redirected to the User portal of the originator Centre to perform his request. (Show information message that user will be redirected elsewhere)
REQ177 - Product instances | 0 | Medium |  | 0 | OPENWIS-SSD-249 OpenWIS must allow to select product instances for Global product, if the metadata contains one of the following information: - temporal extent expressed as a full date and a regular recurrence frequency - update frequency for the data In case of conflicting information, the update frequency prevails (Provide a better UI component for this. [only if there is time information in the metadata, otherwise disable]) | NOT REQUIRED When subscribing, the user gets ALL the data
REQ178 - Product instances widget | 0 | Medium |  | 0 | OPENWIS-SSD-250 When product instances can be inferred from metadata information, OpenWIS must present a graphical widget to select these instances, depending on the number of configurable results. | NOT REQUIRED When subscribing, the user gets ALL the data
REQ179 - Distribution parameters | 1 | Medium |  | 5 | OPENWIS-SSD-251 OpenWIS must support the definition of primary and secondary distribution parameters. The secondary distribution parameters will be used if the primary distribution fails.
REQ180 - Distribution alternatives | 1 | Medium |  | 0 | OPENWIS-SSD-252 Distribution parameters must include the following set of distribution alternatives: MSS/FSS, RMDCN dissemination, Public dissemination and download. | Included in REQ179
REQ181 - Distribution alternatives modification | 1 | Medium |  | 0 | OPENWIS-SSD-253 OpenWIS must be extensible enough to be able to integrate a new distribution alternative or remove an existing one. | Included in REQ179
REQ182 - RMDCN dissemination | 1 | Medium |  | 2 | OPENWIS-SSD-256 RMDCN dissemination alternative must be proposed to the user only if: - the user is an Institutional User - the applicable data policy authorizes at least one protocol over the RMDCN network
REQ183 - RMDCN dissemination protocol | 1 | Medium |  | 0 | OPENWIS-SSD-257 RMDCN dissemination alternative must allow the user to choose between the two disseminaton protocols: FTP and Email, provided they are authorized by the applicable data policy. | Included in REQ182
REQ184 - Public dissemination | 1 | Medium |  | 2 | OPENWIS-SSD-258 Public Dissemination alternative must be proposed to the user only if: - the applicable data policy authorizes at least one protocol over the Public network
REQ185 - Public dissemination protocol | 1 | Medium |  | 2 | OPENWIS-SSD-259 Public Dissemination alternative must allow the user to choose between the two diffusion protocols: FTP and Email, provided they are authorized by the applicable data policy.
REQ186 - FTP protocol parameters | 1 | Medium |  | 2 | OPENWIS-SSD-260 OpenWIS must allow the user to define the following required parameters in association to the FTP protocol: - Host (mandatory) - Path (mandatory) - User (mandatory) - Password (mandatory) (Verify connectivity [procedural thing]) | Includes the connectivity verification ( uses REQ179)
REQ187 - FTP protocol advanced parameters | 1 | Medium |  | 2 | OPENWIS-SSD-261 OpenWIS must allow the user to define the following advanced parameters in association to the FTP protocol, that must not be displayed by default: - Port - Passive (default) / Active mode - Whether a check on file size must be performed after transfer - Encryption (optional) | Reuses REQ186
REQ188 - FTP protocol stored configuration | 1 | Medium |  | 4 | OPENWIS-SSD-263 OpenWIS must allow the user to select a stored configuration (favourite) for the FTP protocol. Once a configuration selected, OpenWIS will fill the stored FTP parameters associated to this configuration. (Let users specify a name for a favorite and allow multiple favorites for a single host.)
REQ189 - FTP protocol alternative favorites | 1 | Medium |  | 0 | OPENWIS-SSD-264 OpenWIS must allow the user to store (as favourite) the FTP parameters that are currently edited in association to a particular distribution alternative. | Included in REQ188
REQ190 - Email protocol parameters | 1 | Medium |  | 0 | OPENWIS-SSD-265 OpenWIS must allow the user to define the following required parameters in association to the Email protocol: - Email address (mandatory) | Included in REQ179
REQ191 - Email protocol advanced parameters | 1 | Medium |  | 3 | OPENWIS-SSD-266 OpenWIS must allow the user to define the following advanced parameters in association to the Email protocol, that must not be displayed by default: - Header line, that must be added to the email header - Whether the email recipient receives the email directly (TO), receives only a courtesy copy (CC) of the email, or receives only a blind copy of the email (is not mentioned in the email header) (NONE: default) - Subject of the email - Whether the file must be sent as attachment or embedded in Body - File name, to precise the name of the attached product file name - Add tooltip that explains what header is
REQ192 - Email protocol stored configuration | 1 | Medium |  | 2 | OPENWIS-SSD-267 OpenWIS must allow the user to select a stored configuration (favourite) for the Email protocol. Once a configuration selected, OpenWIS will fill the stored Email parameters associated to this configuration.
REQ193 - Email protocol alternative favorites | 1 | Medium |  | 0 | OPENWIS-SSD-268 OpenWIS must allow the user to store (as favourite) the Email parameters that are currently edited in association to a particular dissemination alternative. (Improve stuff) | Included in REQ192
REQ194 - HTTP download | 1 | Medium |  | 0 | OPENWIS-SSD-269 HTTP Download alternative is available only on a public (not RMDCN) deployment of OpenWIS. | Included in REQ034
REQ195 - Ad-hoc request wizard steps | 1 | Medium |  | 0 | OPENWIS-SSD-270 OpenWIS must allow the creation of a new ad-hoc request through a 4 step wizard: Step 1: definition of sub-selection parameters (for the ad-hoc request) Step 2: definition of primary distribution parameters Step 3: definition of secondary distribution parameters (optional) Step 4: request acknowledgment | To be further analysed during Use Cases phase
REQ196 - Subscription request wizard steps | 1 | Medium |  | 0 | OPENWIS-SSD-271 OpenWIS must allow the creation of a new subscription through a 4 step wizard: Step 1: definition of sub-selection parameters (for the subscription request) and scheduling of the subscription Step 2: definition of primary distribution parameters Step 3: definition of secondary distribution parameters (optional) Step 4: request acknowledgment | To be further analysed during Use Cases phase
REQ197 - Subscription on product arrival | 1 | Medium |  | 1 | OPENWIS-SSD-272 OpenWIS must allow the user to create a subscription based on product arrival | Reuses REQ196
REQ198 - Search results | 1 | Medium |  | 0 | OPENWIS-SSD-232 After a simple or an advanced search, the results must be presented as a list of metadata. The following information must be shown for each metadata: - Title - Abstract (part of) - Keywords (part of) - Thumbnail (optional, if documented in the metadata) - Logo (identifying the source for example, if documented in the metadata) - 'Draft' status when the metadata is a stop-gap metadata (Accordion layout) | Included in REQ048
REQ199 - Search result actions | 1 | Medium |  | 0 | OPENWIS-SSD-233 Actions must be associated to each metadata result: - View metadata detail - Create/Edit/Delete Metadata (authorized users only) - Perform Ad-hoc request and Subscribe request (authorized users only) - Manage associated privileges (authorized users only) | To be further analysed during Use Cases phase
REQ200 - Simple search component | 1 | Medium |  | 0 | OPENWIS-SSD-229 The simple search component must propose: - a text field for full-text search - a bounding box as map search tool | To be further analysed during Use Cases phase
REQ201 - Metadata creation steps | 1 | Medium |  | 0 | OPENWIS-SSD-274 The User portal must allow an Editor to create new metadata with the following steps: 1. Choose one of the available metadata templates 2. Choose groups the metadata will belong to 3. Define the unique metadata identifier (fileIdentifier) 4. Create the initialized (according to template) metadata 5. Open the metadata in the Metadata Editor (Not currently supported)
REQ202 - Metadata identifier compliance | 1 | Medium |  | 0 | OPENWIS-SSD-275 The widget allowing to define the metadata identifier must constrain the user to comply with OpenWIS URN pattern for fileIdentifier. | Included in REQ048
REQ203 - Metadata import support | 1 | Medium |  | 0 | OPENWIS-SSD-276 Metadata import must be supported | Non-Functional
REQ204 - Metadata list view | 1 | Medium |  | 1 | OPENWIS-SSD-277 OpenWIS must allow an Editor to display a (sort-able &amp; filterable) list of metadata he has created (or imported), showing the following information for each metadata: - metadata ID (URN) - metadata title - GTS Category - AHL pattern or overridden AHL pattern if any - FNC pattern or overridden FNC pattern if any - GTS priority - Data policy or overridden data policy if any - Local Data source where the data come from | Reuses REQ123
REQ205 - Metadata browsing actions | 1 | Medium |  | 2 | OPENWIS-SSD-278 Browsing his metadata, an Editor must be able to: - view the details of a selected metadata - remove selected metadata - export selected metadata | Reuses REQ125
REQ206 - Track my requests page actions | 1 | Medium |  | 2 | OPENWIS-SSD-279 On the 'Track my Requests' page, a user must be able to monitor and manage its recent and current ad-hoc requests and its current subscriptions. | Reuses REQ112
REQ207 - Recent ad-hoc requests panel | 1 | Medium |  | 2 | OPENWIS-SSD-280 The Recent Ad-hoc requests panel must show all the ad-hoc requests performed by the user, contained in the System. For each request the following information must be shown: - metadata title - metadata FileIdentifier - request number - creation date - request status, in association to a representative icon | Reuses REQ112
REQ208 - Ad-hoc request disposal | 1 | Medium |  | 2 | OPENWIS-SSD-281 The user must be able to discard an ad-hoc request to remove permanently the request from the System. | Reuses REQ112
REQ209 - Ad-hoc request metadata linking | 1 | Medium |  | 2 | OPENWIS-SSD-284 The user must be able to navigate to the metadata for the (ad-hoc) requested product.
REQ210 - Ad-hoc request details | 1 | Medium |  | 4 | OPENWIS-SSD-285 The user must be able to view the details of an ad-hoc request, displaying the following information in a compact way: - Sub-selection parameters selected for the request - Chosen distribution options - History of status changes
REQ211 - Subscriptions panel | 1 | Medium |  | 2 | OPENWIS-SSD-286 The Subscriptions panel must show all user subscriptions contained in the System. For each subscription the following information must be shown: - metadata title - metadata FileIdentifier - request number - creation date - last processing time - the last results, in association to an icon representing the status of each result (the last status) | Reuses REQ042
REQ212 - Subscription disposal | 1 | Medium |  | 2 | OPENWIS-SSD-287 The user must be able to discard a subscription to remove permanently the subscription from the System, as well as the associated results | Reuses REQ042
REQ214 - Subscription control | 1 | Medium |  | 2 | OPENWIS-SSD-288 The user must be able to suspend an active subscription and resume a suspended subscription. | Reuses REQ042
REQ215 - Download product for failed subscription delivery | 1 | Medium |  | 2 | OPENWIS-SSD-289 The user is able to download the product instance(s) when the last completed results of a subscription was a failure from the 'Track my Requests' page. If the data is still in the cache they can download it by an ad hoc HTTP download.
REQ216 - Navigation to product metadata | 1 | Medium |  | 2 | OPENWIS-SSD-290 The user must be able to navigate to the metadata for the subscribed product.
REQ217 - Subscription details modification | 1 | Medium |  | 2 | OPENWIS-SSD-291 The user must be able to modify the details of a subscription. | Reuses REQ042
REQ218 - Subscription details view | 1 | Medium |  | 5 | OPENWIS-SSD-292 The user must be able to view the details of a subscription, displaying the following information in a compact way: - Sub-selection parameters that have been selected for the subscription - Size of chosen instances if readily available - Chosen distribution options - Scheduling options - History of the subscription status changes - History of the last processing results - Possibly hyperlink to backup subscription made at other GISC | Reuses REQ042
REQ219 - Subscription result expiry | 1 | Medium |  | 2 | OPENWIS-SSD-293 The result of a 'last processing' for a subscription must expire after a configurable period. Expired results are removed from the System, with all associated product instances.
REQ220 - User info management | 1 | Medium |  | 10 | OPENWIS-SSD-296 A user must be able to manage his personal information | We will provide an API that will allow transparent user management for both local and SSO scenarios
REQ221 - User favorite configurations view | 1 | Medium |  | 5 | OPENWIS-SSD-297 A user must be able to see the list of their favourite distribution configurations. Each configuration is associated to a distribution alternative.
REQ222 - User favorite configurations management | 1 | Medium |  | 5 | OPENWIS-SSD-298 A user must be able to create, edit and remove a favourite distribution configuration.
REQ223 - Group management | 1 | Medium |  | 0 | OPENWIS-SSD-169 An AccessAdmin must be able to create, remove, modify the details of a group. | Included in REQ137, we will provide an API
REQ224 - Local authentication | 1 | Medium |  | 12 | OPENWIS-SSD-155 OpenWIS must support local authentication for a known user (Except when external SSO exists).
REQ225 - Authentication mechanism | 1 | Medium |  | 10 | OPENWIS-SSD-157 OpenWIS will be provided with a user/password based scheme for authentication; the underlying system must be extensible enough to support future integration other authentication mechanisms.
REQ226 - Machine to machine authentication | 1 | Medium |  | 7 | OPENWIS-SSD-162 OpenWIS must support a machine-to-machine authentication.
REQ227 - User management | 1 | Medium |  | 0 | OPENWIS-SSD-168 An AccessAdmin must be able to create, remove, modify the details of a user, including access rights. | Included in REQ139
REQ228 - User self-registration | 1 | Medium |  | 0 | OPENWIS-SSD-165 OpenWIS must support user self-registration. | Included in REQ151
REQ229 - Self-registration management | 1 | Medium |  | 0 | OPENWIS-SSD-166 An AccessAdmin must be able to accept/refuse a self-registration request for a user. (Different method. Use of email registration) | Included in REQ151
REQ230 - Self-registration service control | 1 | Medium |  | 0 | OPENWIS-SSD-167 An AccessAdmin must be able to disable self-registration for a given deployment. | Included in REQ151
REQ231 - Web SSO support | 1 | Medium |  | 20 | OPENWIS-SSD-163 OpenWIS must support a Single Sign-On (SSO) mechanism aiming at authenticating the user only once, in the following cases: - User navigates in each authorised part of the portal - User must belong to the class of SSO users
REQ232 - Access control | 1 | Medium |  | 20 | OPENWIS-SSD-174 OpenWIS must check user authorisation before giving access to particular metadata, data or service.
REQ233 - Authorization per user class | 1 | Medium |  | 0 | OPENWIS-SSD-175 Authorisation must only be granted to authenticated users known to the local Centre. Only default limited authorisations will be given to public users (guest). | Non-Functional
REQ234 - Control function access | 1 | Medium |  | 1 | OPENWIS-SSD-177 Only administrator and operator must have access to control functions (see Monitoring and Control section) of the System components.
REQ235 - Subscription management access | 1 | Medium |  | 0 | OPENWIS-SSD-178 Administrators must have access to the management function of subscription details of all users. | Duplicate / subset of REQ042
REQ236 - Request status access | 1 | Medium |  | 0 | OPENWIS-SSD-179 Administrators must have access to the status of ad-hoc and subscription requests. | Duplicate / subset of REQ112
REQ237 - Administrative action status control | 1 | Medium |  | 0 | OPENWIS-SSD-180 All administrative functions must have access control. | Included in REQ232
REQ238 - Responsiveness using TLS | 1 | Medium |  | 0 | OPENWIS-SSD-181 OpenWIS must have acceptable responsiveness even if TLS based protocols are used. | Non-functional
REQ239 - Access policy configuration | 1 | Medium |  | 0 | OPENWIS-SSD-171 OpenWIS must allow the definition and configuration of access policies for each metadata or a group of metadata, and for associated data and services. | Non-functional
REQ240 - User SLA | 1 | Medium |  | 1 | OPENWIS-SSD-172 The User SLA must be represented by a limited number of levels: Gold, Silver and Bronze.
REQ241 - User SLA management | 1 | Medium |  | 4 | OPENWIS-SSD-173 The AccessAdmin must be able to change the SLA associated to a user on the User Management GUI.
REQ242 - TLS support | 1 | Medium |  | 0 | OPENWIS-SSD-170 OpenWIS must allow the configuration of TLS-based transport protocol (HTTPS and FTPS) for metadata and data transfer. When a secured transport is set, it is set for all the metadata and data transfers of the configured Centre. | Non-functional
REQ243 - TCP/IP support | 1 | Medium |  | 0 | OPENWIS-SSD-187 The System must use TCP/IP transport protocol for network communication. | Non-functional
REQ244 - SAML2 SSO | 1 | Medium |  | 0 | OPENWIS-SSD-189 OpenWIS must support exchange of security information with SAML 2.0 | Non-functional
REQ245 - Technology stack | 1 | Medium |  | 0 | OPENWIS-SSD-190 OpenWIS must be based on standard technologies to facilitate deployment in several environments: - Use of Java for server-side application - Use of standard Web technologies (HTML, JavaScript, CSS, ...) - Use of standard well-known container - Use of standard network communication (TCP/IP) | Non-functional
REQ246 - Secure DMZ deployment | 1 | Medium |  | 0 | OPENWIS-SSD-191 OpenWIS must accommodate Partner security constraints (deployment across several secured DMZ). | Non-functional
REQ247 - User role management | 1 | Medium |  |  | OPENWIS-SSD-153 OpenWIS must allow an administrator to manage the User Roles: create, modify and delete a Role. | Included in REQ224 and REQ231
REQ248 - Common understanding of user roles | 1 | Medium |  | 0 | OPENWIS-SSD-154 The common understanding of User Roles corresponds to concerted decisions and actions between administrators of the different involved Centres. | Non-functional
REQ249 - Remote sign-in information logging | 1 | Medium |  | 0 | OPENWIS-SSD-150 During a remote authentication, the system must not log in log files any personal information related to the remote user, but only a technical ID known at the authenticating Centre. | Non-functional
REQ250 - User role mandatory | 1 | Medium |  | 0 | OPENWIS-SSD-146 A User Role is mandatory for a user, and must be assigned during the authentication process. | It is covered in REQ224 and REQ231
REQ251 - User role details | 1 | Medium |  | 0 | OPENWIS-SSD-147 A User Role is composed of: - A user profile: e.g. viewer, editor, administrator - A list of groups: associating specific rights that can be performed on metadata, data and services | Included in REQ225
REQ252 - Private user info | 1 | Medium |  | 0 | OPENWIS-SSD-149 Private information of users must reside inside the system and must not be distributed. | Non-functional
REQ253 - Provided DAR functionality | 1 | Medium |  | 0 | OPENWIS-SSD-022 OPENWIS-SSD-22. OpenWIS must provide DAR functionalities: Discovery: ability to browse and find products and services in a structured catalogue. In our system products and services are described by metadata, stored in a catalogue, which provides a search facility using subject keywords, geographic extent, or temporal range. Access: once a product has been found, access allows a user to specify the way to obtain the relevant data (the product itself or a sub-part). In our system, access can be done defining ad-hoc or subscription requests for authenticated / authorized users. An ad-hoc request is a one-time request; a subscription request is a recurrent request triggered by product arrival or by scheduling basis. Retrieve: refers to the process of delivery of the relevant product(s); in our system it consists in providing the products and the distribution information to the distribution systems. Pending: Definition of "sub-part". | To be further analysed during Use Cases phase
REQ254 - GISC-only deployment | 1 | Medium |  | 0 | OPENWIS-SSD-023 OpenWIS must support a GISC only deployment. | Non-functional
REQ255 - NCPC-only deployment | 1 | Medium |  | 0 | OPENWIS-SSD-024 OpenWIS must support a DCPC only deployment. | Non-functional
REQ256 - NC-only deployment | 1 | Medium |  | 0 | OPENWIS-SSD-025 OpenWIS must support an NC only deployment. | Non-functional
REQ257 - Modularity | 1 | Medium |  | 0 | OPENWIS-SSD-026 System must be modular and must have loosely coupled interfaces between each module. This modular architecture will allow replacement of modules by other implementations. | Non-functional
REQ258 - Local failover | 1 | Medium |  | 0 | OPENWIS-SSD-369 OpenWIS must support local failover mechanisms. | Non-functional
REQ261 - Contribute to GEOSS Clearinghouse | 1 | Medium |  | 0 | Catalogue WIS contributions in the Global Earth Observation System of Systems (GEOSS) Clearinghouse | Get feedback from KMA
REQ262 - Publish data GEOSS | 1 | Medium |  | 0 | Make WMO Resolution 40 (Cg-XII) data available through GEOSS interoperable arrangements | Get feedback from KMA
REQ263 - WIS as a GEOSS component | 1 | Medium |  | 0 | Support WIS as a GEOSS component with a coreΒ role | Get feedback from KMA
REQ264 – Case insensitive Metadata URNs | 1 | Medium |  | 1 | Metadata URNs need to be case insensitive. This is to satisfy WMO Core Metadata Profile version 1.3 and was brought up during TT-GISC 2014 from Toulouse (Paragraph 54 in TT-GISC 2014 Final Report v4).
REQ265 - Sub selection UI | 1 | Medium |  | 0 | In OpenWIS 3, it's possible for local data sources to specify an sub-selection UI that is displayed to the user when they try to make an ad-hoc request or subscribe to the product. An example of this is for retrieving ACCESS-G data from GISC Melbourne (see attached screenshots). I know MF also does something similar. This will need to be supported for OpenWIS 5. At the moment, in OpenWIS 3, there is a single harness for building these sub-selection UIs, making it difficult for separate local data source (LDS) harnesses to have different UI. I'd argue that this harness API should be merged with the local data source API so that each local data source can have their own UI. | To be further analysed during Use Cases phase